## Activity Log_Isolda
Code First Girls - Software Degree ¦ Spring 2023
Name: Isolda |  | Project Group : Recipea ¦ Group 6
This activity log is for you to document your contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions. Or use this as a way to take notes for your own viewing
Week: | Date: | Activity/Task: | Time spent on Activity: | Completed? | Notes:
1 | 2023-04-27 | Meeting with the group outside the class to know the next steps | 15m | Yes | - We talk about the strength of each one. - Daniela brought an idea for a recipe app. - We decided to talk in the next day to have time for those who would like to to have bring some project.
1 | 2023-04-27 | - Create a guide document to organize the next steps. - Add some key tasks on the project so to everyone can assign their selfs as they want. >create git hub >write an about of the project >define well the main features >design the database structure. | 5h | Yes | - As I could not to be in the next day meet I did a project outline so that it was easily adaptable to our project and that during the meeting it was possible to remove or add points that the group found relevant. The purpose of the project is to serve as a basis for thinking about how to divide the tasks among the group. - https://colab.research.google.com/drive/1BWOU5-bdmfxRhD4KcmUT5-UvuyCMFM13?usp=sharing I created a backlog tasks so each one could assign.
1 | 2023-04-28 | - Add Kamo on Slack group - Add tasks on trello that Danielle created | 1h | yes
1 | 2023-04-29 | - Describe for the main features (write some suggestions for the team collaborations and approval. - Created the Google Drive to share the documentation and to allow that everyone can comment and can sugest changes before have a final document. - Share what I did on with the team | 3h | yes | I shared a document try to organize the next steps: - Features (I wrote some suggestions for your collaborations and approval.) - I started creating tasks on Trello. - Documentation - I create a shared google docs to gather information that is not code. https://drive.google.com/drive/folders/1nCxtFhQVYmBzXJ-YHteV5m3O_fVfqTGy As we consolidate the documents we can add it in a folder with final documents.
2 | 2023-05-02 | - Gather and document the sugestions of API to use on our app. - create a poll on slack to choose the API that we will use | 2h | yes
2 |  | From 03rd to 04th - out for grieve reasons
2 | 2023-05-05 | - Homework 2 review and sugestions | 1h | yes | - Some sugestions added to be revied by Danielle and the others: > I improuved the format > Sugested Change DB Edaman - To API Edamam - since we are not accessing their DB. > Sugested From API back-end use only one arrow since we are just receiving info and not writing. or keep both but differenciate write and read from request - response > I add In the last question a text to be edited and add together with Danielle ones.
2 | 2023-05-07 | - I added Danielle's file homework 2 on the google docs. - Add note remembering the the importance of working on the same page and Avoide create duplicates or version conflicts. - resend the googledoc link | 20m | yes
3 | 2023-05-09 | - create Github - add collaborators - create questions to understand better the app behaviour and to the build the steps with more base. | 20m | yes | I am starting my work and situate myself on the project but I still have some questions about it. I think it will be easier for me to have things clear in my head before continuing. I will list them in no particular order, I hope we can discuss it in our next meeting: - can we have wireframes for the main screens? - when a user searches for a recipe, will both edamam and the ones uploaded by the user be displayed together? - we have endpoints of the app? we should define them so we know the basic behaviour of the app (I will work on that) - is anyone working on the database design? we need to define the tables, columns, types, etc. - I would like to know more details about the matching system. how does it work? what are the criteria for the match to happen? - if we don’t have user authentication, how will we match users X recipes? - should we create an initial list of tags? - will we adopt the name used in the design (recipeo_). I like it. - what is the “heart” symbol next to the search bar? - what framework will be used in the frontend?
3 | 2023-05-11 | - review Danielle DB proposal - Commented on the DB programing and suggested add some tables and review the image proposal. - rewrite roadmap and distribute tasks for eachone assign what want | 90 | yes | Answering Danielle and Raluca together because it's complementary Thanks Dani for setting up the SQL database for our recipe app. I understood your point in making it simpler and I understand we have limited time to complete the MVP, I am also afraid about the time and complexity to develop the app. but since it is our final project I believe It’s important to strike a balance between simplicity and functionality. So, I’d like to suggest a couple of additions to make our app even better. Health Restrictions: maybe to include a column for health restrictions in the recipe_data table. This column can store information such as vegetarian, vegan, gluten-free, dairy-free, etc. It will allow users to filter recipes based on their specific dietary needs. Maybe we can think about Ingredients and quantities can be another table. In my opinion, searching by ingredient is essential. We have a field to send a picture in the wireframe, so if we want to implement it we need to add a column for this field in the table. These are just suggestions, but I fully understand the choice you make. Hey there, Raluca! I wanted to take a moment to appreciate the excellent job you’ve done. It shines! Just to see if we are all in the same page: 1.0 Main page. Go: Take the user to Build your perfect match base. What does the top search bar do? Send yours: takes user to the recipe upload page 2.0 Build your perfect match base. The user selects the tags and clicks in go - takes the user to Matches (search results) maybe use search in place of got can be clearer to the user? These tags we can find in the Edman right? We want to use tags with the internal recipes, we will probably need another table on the DB. What is the research criteria? Are we going to search by tags (health restriction, cuisine, meal type), ingredient as well? In my view, searching by ingredients is essential. 3.0 Matches - you can expand the card. Could you explain how the match mechanism works? Is it a like? If you click on the heart on the top right what will be displayed? What does the “x” button do? The like will not be in the back-end? Will we use local storage in the front-end, is it right? Portion is in the DB so we can use in the framework(or not use in the DB). 4.0 Recipe upload We have a field to send a picture, so we need to add a column for this field in the table.
3 | 2023-05-12 | - Design the endpoint documentation - Call with review with Daniela points of the Homework 2- | 40 | yes | - I design a first draft for the endpoint - waintg comments of the team: https://docs.google.com/document/d/1lBkK0xG9OpIJ9ZPOvJ7dw7_tQfOFlyiv/edit?usp=sharing&ouid=117340744786620765016&rtpof=true&sd=true - reinforce my comments about homework 2 that was not implemented.
3 | 2023-05-14 | Review Danielle Data Base, writing code using the previous sugestions and arguments. | 45min | yes | I code the sugestion that I did before tring to collaborate and And to turn possible starting implementing the routes and share the back-end tasks.
4 | 2023-05-15 | - Added new tables and did some suggestions. - add file on github and did a pull request to the team. - added my tasks on Trello | 1h35m | yes
4 | 2023-05-17 | - reviewing API + DB clases, searching about API and DB on internet | 2h
4 | 2023-05-18 | - Searching about Flask application and folder structure - implementing a folder structure | 3h | yes
4 | 2023-05-19 | - Homework 3 Search recipes on Edamam API - Declared the endpoint routes for search edaman and add recipe | 6h | yes
4 | 2023-05-20 | Search recipes on Edamam API - Back-end development, creating methods to get data from Edamam API - Data validation, cleaning (results of data from API) Add recipes on our Database - Declared the endpoint routes - Back-end development, creating methods to add data on the Database | 6h | yes
4 | 2023-05-21 | - Meet Ella 11am - to know about the console buiding and code and others routes she is doing - Mee the group 1pm - sugested a distribution task / presenting folder structure and the routes created. - Write Read me with instructions and arquitecture of the app. - upload project on git hub and merging in main (for the other implement the others routes) | 4h | yes | - Update the main branch
5 | 2023-05-23 | - implement the console that Ella created and integrate it with the API - I neede to recode part of it to fit with the structure of our DB | 4h |  | Workin in the console with Ella's code: ** Since her branch was not actualised with the main branch, the best soluction that I found to avoid conflict was copy her code and work on the console branch. It Was necessary change a bit the proposal to working accordingly with the Database's structure.
5 | 2023-05-24 | out - doing homework 4
5 | 2023-05-25 | - review Liddias's search DB function - Ask Follow up Raluca / Ella / Lidiia sinse I coud not be in the meeting in the previous day - Study, write and shared some tips with mesures to avoiding code conflicts and to use architecutre patters and integration | 2h | yes | Sugestions to integrate what Lidiia did with the rest of the API architecture: - Implement the function that you created in app/api/recipea_db.py - Create the route search_db (on app/routes/api_routes.py), import the function you created in the previous step and use it in the endpoint - Follow the same pattern/architecture in the app, properly separating the endpoints, db access and the main logic So After that I can work on integrating it with the console part. ----- Share some cool GitHub tips I recently picked up. These might come in handy as we work together: 1. Branch naming: It’s a good practice to name new branches after the feature they represent. It helps us keep track of things easily: E.g. delele_route, delete_function 2. Up-to-date branches: Working on a new feature it’s good practice to create a new branch from the most actualised main branch to avoid future conflict. Just a heads up, it would be awesome if you In the new features that you are working on (delete route / delete function), could integrate it with the latest changes from the main branch, so when you send as a pull request it will be integrated and updated.
5 | 2013-05-25 | - Add log document to the googledocs |  |  | - https://docs.google.com/spreadsheets/d/1OW_GI1BSOF3x5N8JnVF9JI0cZMChcMrp/edit?usp=sharing&ouid=117340744786620765016&rtpof=true&sd=true
5 | 2023-05-26 | - Review Raluca's pull request > update recipe | 20min | yes | - I did just one suggestion for change that is delete the file update_recipe.py file, since the code is already integrated in the recipea_db file. She did the modification and I merged the code on the main branch.
5 | 2023-05-26 | - Review Ella's pull request > delete recipe | 1h | yes | > recipe_app.py file > we have a Pull Request called "console" that moves this logic to recipea/app/console and with some adjustments to integrate it with the rest of the application. If you want to keep this file, I think the best place for it is the folder I just mentioned. This folder is not yet in the main branch, it will appear after we merge the PR. > Ideally we should use the primary key or a unique field (recipe_ID) to do the DELETE, since we can sometimes have more than an recipe with the same name. To follow a pattern, Raluca used a parameter in the URL to do the update, so my suggestion is that we follow this same idea. Like this: @api_routes.route('/recipes/int:recipe_id’). > With the latest changes to the DB, having the recipes, ingredients and recipes_ingredients tables, we cannot delete from recipes directly if we have matching records in recipes_ingredients. We need to delete from recipes_ingredients first and then from ingredients. I also changed from recipe_name to recipe_ID (the input parameter has to be changed), as mentioned in my comments in api_routes. Here's the updated code as a reference:
5 | 2023-06-26 | - Review Lidiia's branch | 30m |  | Some points that we can see together: > there are no parameters on the route. the search term(s) should come as parameters like we did on the `search_recipe_edamam` endpoint. > we cannot have input() in an API call, otherwise it will block the execution. we should use parameters from the API call instead, like mentioned in another comment. > The query is not taking into account the relationship between the tables. please refer to `recipe/app/db/schema/Recipea_App_User_Fed_DB.sql` > We need a `return` statement at the end of `search_recipe`, so the returned values go to the routes file.
5 | 2023-05-26 | - Pair programming with lidia | 2h | yes | > review the main issues - search some solutions > Work together with Lidiias on her code.
5 | 2023-05-27 | - follow up the final deliverys - help the other with teir needs | 2h | yes | > Sent message for Liddia / help her with the final document > Know how Elisabeth and Ella is going in their work.
5 | 2023-05-27 | - documentatiom | 3h | yes
5 | 2023-05-27 | - work in pair with Ella | 30m | yes | >
5 | 2023-05-27 | - solve conflicts - pull request Delete and merge to main | 30m | yes
5 | 2023-05-28 | - check tests - edaman - | 1h30 | yes
5 | 2023-05-28 | - review documentation | 3 | yes
5 | 2023-05-28 | - solve conflicts lasts pull requests | 1 | yes
5 | 2023-05-28 | - add log to the documentation. | 10 | yes
5 | 2023-05-28 | - add tests to documentation | 30 | yes
5 | 2023-05-28 | - pull request |  | yes
Other tasks to do:
> restructure folder arquitecture including Tests folder
> include Tests on the README

## Activity Log_Danielle
Name: | Danielle Lott | Project Group (Name/Number): Recipea / 6
This activity log is for you to document your contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions. Or use this as a way to take notes for your own viewing
Week: | Date: | Activity/Task: | Time spent on Activity: | Completed? | Notes:
1 | 27.4.2023 | Group on Slack and Whatsapp Created, started to decide theme of the project, introductions, gauging of our experiences | 30 minutes | No
1 | 28.04.23 | Group meeting on Zoom: Project Theme Decided | 30 minutes | Yes | Matching Recipes App
2 | 02.05.23 | Group Meeting for API to be used and how to proceed with project | 25 minutes | No | Important progress was achieved and it was put up for voting which API would be used on the Slack group, Edamam won.
2 | 03.05.23 | Group Meeting for more details on how to develop the project | 45 minutes
2 | 05.05.23 | Draft of the HW file and Diagram of how it would work | 2 hours | Yes | What was completed was the Draft for the other group members to check.
3 | 07.05.23 | First Draft of the User DB. | 2 hours | Yes
3 | 10.05.23 | Group Meeting for Raluca to show her design concept for the project and for me to show the first draft of the User Fed DB. | 30 minutes | Yes | Many changes were requested, so it was fruitful.
3 | 11.05.23 | Worked on a second and third Drafts as per requested changes. | 2 hours | No | Some difficulties with choosing the best option for "Image" between VARCHAR with link and VARBINARY
3 | 12.05.23 | Worked on finalizing the second and third drafts. | 5 hours | Yes | Submitted for group input and choice and evaluation
4 | 15.05.23 | Group Meeting to update on final adjustments of needed for DB and works on Back End | 20 minutes | Yes
4 | 17.05.23 | Worked on finalizing DB, created ER diagram and ansewered some questions from Responsible Instructor. | 5 hours | Yes
5 | 21.05.23 | Group Meeting to update status of the Endpoints development and check what can be further done. | 38 minutes | Yes | It was decided that I will also work on the testing and daily meetings will take place
5 | 22.05.23 | Start of Test Making for the Edamam.py file | 2hours | No
5 | 22.05.23 | Group Meeting Status Check | 15 minutes | Yes
5 | 23.05.23 | Start of Test Making for the Recipea_DB.py file, solving some issues of the Test_Edamam file and creating Tests branch | 1 and half hour | No
5 | 23.05.23 | Group Meeting Status Check | 15 minutes | Yes
5 | 24.05.23 | Group Meeting Status Check | 5 minutes | Yes | It was decided to invite our Intructor to the Friday Meeting
5 | 25.05.23 | Group Meeting Status Check | 30 minutes | Yes
5 | 26.05.23 | Group Meeting Status Check | 50 minutes | Yes
5 | 27.05.23 | Test Making for the Edamam, Recipea and API_Routes. | 4h and 35min | No | Awaiting final Ok, from Backend Team for me to go ahead and make the final test and confirm all tests are working. /// Recived the OK to continue, continued until almost 1am, my concentration is breaking and the tests are failing, will go rest for the night and continue in the morning.
6 | 28.05.23 | Finalized all tests for the three files. Finalized input data on logbook. | 3h and 48min | Yes | All tests pass.
Total time:

## Activity Log_Lidiia
Name: | Lidiia Kliuchna | Project Group (Name/Number): Recipea/6
This activity log is for you to document your contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions. Or use this as a way to take notes for your own viewing
Week: | Date: | Activity/Task: | Time spent on Activity: | Completed? | Notes:
7 | 2022-08-16 | Spoke with the group outside of the session to discuss our ideas. Ideas to use for the project are gym membership database | 30 minutes | Yes | EXAMPLE
1 | 2023-04-27 | Discussing with group ideas outside the class | 30 minutes | Yes | Idea was Recipe App
2 | 2023-05-02 | Meeting with the group, discussion of the next steps, searching APIs | 30 minutes | Yes | Chosen Backend Part
2 | 2023-05-03 | Discussion and division of the work. | 30 minutes | Yes
4 | 2023-05-15 | Searching and studying all information of APIs and Flask | 120 minutes | Yes
4 | 2023-05-19 | Starting to work on search part | 4 hours | No | connecting db, trying to find the way to compare user input to db
5 | 2023-05-22 | Continue to work on search | 2 hours | No | connect the table,found the way tonly how to find only by one creteria in db
5 | 2023-05-23 | Continue to work on search | 3 hours | Yes | fixed the problem with connection in db, added seach system be several criterias
5 | 2023-05-24 | Review the code, create PR | 30 minutes | Yes
5 | 2023-05-25 | Started to work on suggestion of Isolda | 2 hours | No | change print to return, remove the input from function, change selecting criteria, created PR
5 | 2023-05-26 | Continue to work on Isolda's suggestion | 2 hours | Yes | implementing of parameters, final PR

## Activity Log_Ella
Code First Girls - Software Degree ¦ Spring 2023
Name: Ella |  | Project Group : Recipea ¦ Group 6
This activity log is for you to document your contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions. Or use this as a way to take notes for your own viewing
Week: | Date: | Activity/Task: | Time spent on Activity: | Completed? | Notes:
2 | 2023-05-02 | Reasearched project ideas as well as potential API we could use to extract infromation for our application. Research backend features for the applications as volunteer to help with this part of the project. | 2hrs | Y
3 | 2023-05-14 | Started working on the back end console application | 3hrs | Y | - The code pulls recipes from the Edamam API based on user input. - Users can search for recipes by specifying an ingredient, cuisine, meal type, and food allergies. - The code makes an API request to Edamam to retrieve a list of matching recipes. - Each recipe's details, including name, ingredients, and url to cooking instructions, are displayed to the user. - Users have the option to save a recipe to a database if they like it. - If a recipe is not saved, the code moves on to the next recipe in the list. - MySQL was used to store saved recipes. - The code aims to provide personalized recipe recommendations and allows users to build their own curated recipe collection. - The integration of the Edamam API enhances the cooking experience by offering diverse and relevant recipe options.
4 | 2023-05-20 | Continued working on the back end console application | 5hrs | Y | - Establishing a connection between a console app and a MySQL database created by a team member. - Implementing interactive communication within the console app to prompt and request user inputs. - Capturing and validating user inputs in the console app to ensure they meet the required criteria. - Handling errors or exceptions that may arise during the communication between the console app and the database.
4 | 2023-05-21 | Meeing with Isolda @ 11am to discuss progress on backend develoupment Meeting with Group @ 1pm to talk though progress on backend develoupment and split remaining tasks | 2hrs | Y | - The console app was not written using a version control system (VCS). - Discussed the implementation of VCS to manage and track code changes in the console app. - Discussed the file structure of the console app, ensuring it is organised and follows best practices. - Reviewed the remaining tasks that need to be completed for the console app. - Discussed timelines and set goals to complete the remaining tasks in a timely manner.
5 | 2023-05-23 | Created a delete function that allowed you to delete receipe from database using reipe name | 2hrs | Y
| 2023-05-24 | Created a pull request on GitHub so that team members could check work befor merging to the main branch. Attended a daily stand up meeting | 15 mins | Y
| 2023-05-26 | Check Isoldas implementation of console code in to main code. | 15 mins | yes
Other tasks on the back log:

## Activity Log_Elizabeth
Name: | Elizabeth Turay | Project Group (Name/Number): Group 6
This activity log is for you to document your contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions. Or use this as a way to take notes for your own viewing
Week: | Date: | Activity/Task: | Time spent on Activity: | Completed? | Notes:
7 | 2022-08-16 | Spoke with the group outside of the session to discuss our ideas. Ideas to use for the project are gym membership database | 30 minutes | Yes | EXAMPLE
| 2023-04-28 | Discussed what everyone's strengths were and what we would like to do. | 30 minutes | yes | I'm doing some frontend
| 2023-05-02 | Further discussed what ideas we should do with out project | 30 minutes | yes | Decided on a recipe page
| 2023-05-10 | Speak about hw2, hearing raluca's design and danielle's user feed DB | 30 minutes | yes | Clarified duties
| 2023-05-15 | Checking in on progress | 30 minutes | yes | Clarified duties
| 2023-05-17 | Received design from Raluca and began basic HTML | 2+ hours | yes | Frontend
| 2023-05-19 | Continued working on frontend and implenting javascript functions | 2+ hours | yes | Frontend
| 2023-05-21 | Checking in on progress | 30 minutes | yes | Caught up on progress
| 2023-05-22 | Checking in on progress | 30 minutes | yes | Caught up on progress
| 2023-05-23 | Checking in on progress | 30 minutes | yes | Caught up on progress
| 2023-05-24 | Checking in on progress | 30 minutes | yes | Caught up on progress
| 2023-05-25 | Checking in on progress approaching deadline | 30 minutes | yes | Caught up on progress
| 2023-05-26 | Began finishing touches on the project website and caught up with what the team were uploading to the github | 5+ hours | yes | Frontend
| 2023-05-27 | Continued working on frontend and implenting javascript functions | 5+ hours | yes | Frontend
| 2023-05-28 | Uploaded the majority of what I could complete to github repo and I will try to implement backend in my own time after the course | 3+ hours | yes | Frontend
Total time:

## Activity Log_Raluca
Name: | Raluca Teslovan | Project Group (Name/Number): Group 6
This activity log is for you to document your contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions. Or use this as a way to take notes for your own viewing
Week: | Date: | Activity/Task: | Time spent on Activity: | Completed? | Notes:
| 2023-04-27 | We've been assigned to our group, each member stated their strengths and/or what they want to work on. | 30 minutes | yes | -
| 2023-05-28 | Meeting during which we have discussed our ideas for the project | 30 minutes | yes | Decision on the final idea to be discussed in the next meeting
| 2023-05-02 | Decided we will proceed with a Recipe-based dating app, team started doing research on best API's to use for our project, we decided on using Edamam API | 30 minutes | yes | -
| 2023-05-03 | Started crafting the UI/UX for the website along with logo, wireframes and visual image of frontend | ~11 hours | yes | to be presented to the team
| 2023-05-10 | Presented the UI/UX design idea to the team | 30 minutes | yes | Team approved of design - backend next
| 2023-05-10 | Sent the files to Elizabeth for Frontend purposes | 30 minutes | yes | Frontend
| 2023-05-15 | Checcking in on progress | 30 minutes | yes | Ella showed us her piece of code for one of the user-fed API we're building
| 2023-05-21 | Checking in on progress | 30 minutes | yes | Caught up on progress
| 2023-05-22 | Started developing the code for the update_recipe function in the user fed API + endpoint route - sent in the code and did a PR on GitHub | ~5 hours | yes | Backend, tested the code on my machine, fully functional
| 2023-05-25 | Checking in on progress | 30 minutes | yes | Caught up on progress
| 2023-05-24 | Checking in on progress | 30 minutes | yes | Caught up on progress
| 2023-05-25 | Checking in on progress approaching deadline | 30 minutes | yes | Caught up on progress
Total time: